## Sheet1
Namn | Tot. tim.
Fredrik | 21
Niklas | 11.5
Anders | 11
Sofie | 3
Rene | 19
|  | Datum | Timmar | Namn | Vad har jag gjort
|  | 2013-03-21 | 1 | Niklas | Startup Meeting
|  | 2013-03-21 | 1 | Fredrik | Startup Meeting
|  | 2013-03-21 | 1 | Rene | Startup Meeting
|  | 2013-03-21 | 1 | Sofie | Startup Meeting
|  | 2013-03-21 | 1 | Anders | Startup Meeting
|  | 2013-04-15 | 2 | Fredrik | Setting up database
|  | 2013-04-15 | 2 | Anders | Setting up map
|  | 2013-04-16 | 3 | Fredrik | Getting the map to work properly. And also testing the database. Also added a few settings on the map.
|  | 2013-04-17 | 2 | Sofie | Emailed all sections, sought out working logos, setup of project
|  | 2013-04-17 | 3 | Anders | Bound map to campus
|  | 2013-04-15 | 1 | Rene | Meeting
|  | 2013-04-15 | 1 | Anders | Meeting
|  | 2013-04-15 | 1 | Niklas | Meeting
|  | 2013-04-15 | 1 | Fredrik | Meeting
|  | 2013-04-14 | 1 | Anders | User stories
|  | 2013-04-18 | 2 | Anders | Added min-zoom level
|  | 2013-04-18 | 4 | Fredrik | Research on fancy menu but ended with implemented basic one.
|  | 2013-04-19 | 2 | Fredrik | Meeting and coding
|  | 2013-04-20 | 4 | Fredrik | Database and learning and implementing unittests
|  | 2013-04-23 | 4 | Fredrik | Coding querys
|  | 2013-04-19 | 3 | Niklas | App logo and reading up on design
|  | 2013-04-23 | 0.5 | Niklas | Looking over some work and reading on design
|  | 2013-04-24 | 3 | Niklas | Implementing menu system and reading up on search interfaces
|  | 2013-04-16 | 2 | Niklas | Reading up on android, setting up system so forth
|  | 2013-04-16 | 5 | Rene | printing Maps, added Rooms from EDIT building and Lärsalsvägen, looked up coordinates
|  | 2013-04-17 | 3 | Rene | added Rooms from Architecture Building, looked up coordinates
|  | 1900-01-17 00:59 | 2 | Rene | added Rooms from Grouproom building behind EDIT
|  | 2013-04-19 | 1 | Rene | Meeting
|  | 2013-04-19 | 1 | Anders | Meeting
|  | 2013-04-19 | 1 | Niklas | Meeting
|  | 2013-04-21 | 2 | Rene | Research on Google Maps
|  | 2013-04-24 | 2 | Rene | Research on Android, reading through Database Code, making an ER-Diagram, tried to understand git
|  | 2012-03-21 | 2 | Rene | Setup of git repo, schedule, etc