## Sheet1
Namn | Tot. tim.
Fredrik | 63
Niklas | 34
Anders | 50
Sofie | 29
Rene | 27
|  | Datum | Timmar | Namn | Vad har jag gjort
|  | 2013-03-19 | 2 | Sofie | Looking up and setting up gitHub and Eclipse with help of friend
|  | 2013-03-21 | 1 | Niklas | Startup Meeting
|  | 2013-03-21 | 1 | Fredrik | Startup Meeting
|  | 2013-03-21 | 1 | Rene | Startup Meeting
|  | 2013-03-21 | 1 | Sofie | Startup Meeting
|  | 2013-03-21 | 1 | Anders | Startup Meeting
|  | 2013-04-15 | 2 | Fredrik | Setting up database
|  | 2013-04-15 | 2 | Anders | Setting up map
|  | 2013-04-16 | 3 | Fredrik | Getting the map to work properly. And also testing the database. Also added a few settings on the map.
|  | 2013-04-17 | 2 | Sofie | Emailed all sections, sought out working logos, setup of project
|  | 2013-04-17 | 3 | Anders | Bound map to campus
|  | 2013-04-15 | 1 | Rene | Meeting
|  | 2013-04-15 | 1 | Anders | Meeting
|  | 2013-04-15 | 1 | Niklas | Meeting
|  | 2013-04-15 | 1 | Fredrik | Meeting
|  | 2013-04-14 | 1 | Anders | User stories
|  | 2013-04-18 | 2 | Anders | Added min-zoom level
|  | 2013-04-18 | 4 | Fredrik | Research on fancy menu but ended with implemented basic one.
|  | 2013-04-19 | 2 | Fredrik | Meeting and coding
|  | 2013-04-20 | 4 | Fredrik | Database and learning and implementing unittests
|  | 2013-04-23 | 4 | Fredrik | Coding querys
|  | 2013-04-19 | 3 | Niklas | App logo and reading up on design
|  | 2013-04-23 | 0.5 | Niklas | Looking over some work and reading on design
|  | 2013-04-24 | 3 | Niklas | Implementing menu system and reading up on search interfaces
|  | 2013-04-16 | 2 | Niklas | Reading up on android, setting up system so forth
|  | 2013-04-16 | 5 | Rene | printing Maps, added Rooms from EDIT building and Lärsalsvägen, looked up coordinates
|  | 2013-04-17 | 3 | Rene | added Rooms from Architecture Building, looked up coordinates
|  | 1900-01-17 00:59 | 2 | Rene | added Rooms from Grouproom building behind EDIT
|  | 2013-04-18 | 1.5 | Sofie | Mailing, researching documentation, logos
|  | 2013-04-19 | 1 | Rene | Meeting
|  | 2013-04-19 | 1 | Anders | Meeting
|  | 2013-04-19 | 1 | Niklas | Meeting
|  | 2013-04-21 | 2 | Rene | Research on Google Maps
|  | 2013-04-24 | 2 | Rene | Research on Android, reading through Database Code, making an ER-Diagram, tried to understand git
|  | 2012-03-21 | 2 | Rene | Setup of git repo, schedule, etc
|  | 2013-04-26 | 5 | Fredrik | Added unit tests for every function in DAO. Helping with git
|  | 2013-04-27 | 5 | Fredrik | Adding suggestionsfunction and learning a lot about searches. Took longer than expected.
|  | 2013-04-29 | 1 | Anders | Bug fix: init point and zoom
|  | 2013-04-28 | 2 | Fredrik | Insert Data
|  | 2013-04-26 | 2 | Niklas | Meeting 2 with Supervisor Max
|  | 2013-04-26 | 2 | Anders | Meeting 2 with Supervisor Max
|  | 2013-04-26 | 2 | Fredrik | Meeting 2 with Supervisor Max
|  | 2013-04-26 | 2 | Rene | Meeting 2 with Supervisor Max
|  | 2013-04-26 | 2 | Sofie | Meeting 2 with Supervisor Max
|  | 2013-04-19 | 2 | Niklas | Meeting 2 with Supervisor Max
|  | 2013-04-19 | 2 | Anders | Meeting 2 with Supervisor Max
|  | 2013-04-19 | 2 | Fredrik | Meeting 2 with Supervisor Max
|  | 2013-04-19 | 2 | Rene | Meeting 2 with Supervisor Max
|  | 2013-04-29 | 1 | Sofie | meeting
|  | 2013-04-29 | 1 | Niklas | meeting
|  | 2013-04-29 | 1 | Anders | meeting
|  | 2013-04-29 | 1 | Fredrik | meeting
|  | 2013-04-29 | 1 | Rene | meeting
|  | 2013-05-01 | 2 | Anders | Added my position button and upgraded starting point
|  | 2013-05-02 | 4 | Fredrik | Polished search and fixed severe error.
|  | 2013-05-04 | 2 | Fredrik | Learned GUI-tests and added one.
|  | 2013-05-03 | 1 | Anders | Meeting 3 with Max
|  | 2013-05-03 | 1 | Fredrik | Meeting 3 with Max
|  | 2013-05-03 | 1 | Rene | Meeting 3 with Max
|  | 2013-05-05 | 4 | Fredrik | Beginning of paths through buildings
|  | 2013-05-05 | 7 | Anders | Draw path, modified layout, draw line, JSON Parser
|  | 2013-05-05 | 1.5 | Sofie | Structuring documentation
|  | 2013-05-05 | 3 | Anders | Started to parse with ASyncTask distance, duration
|  | 2013-05-06 | 1 | Anders | Regular Monday meeting
|  | 2013-05-06 | 1 | Fredrik | Regular Monday meeting
|  | 2013-05-06 | 1 | Rene | Regular Monday meeting
|  | 2013-05-06 | 1 | Sofie | Regular Monday meeting
|  | 2013-05-06 | 1 | Niklas | Regular Monday meeting
|  | 2013-05-13 | 1 | Anders | Meeting with Max
|  | 2013-05-13 | 1 | Fredrik | Meeting with Max
|  | 2013-05-13 | 1 | Rene | Meeting with Max
|  | 2013-05-13 | 1 | Sofie | Meeting with Max
|  | 2013-05-13 | 1 | Niklas | Meeting with Max
|  | 2013-05-13 | 0.5 | Anders | Error fixing
|  | 2013-05-13 | 0.5 | Anders | Review of documentation
|  | 2013-05-08 | 3 | Anders | Get distance without drawing(not working without async)
|  | 2013-05-13 | 2 | Anders | Exit function and simplied navigation for first version release
|  | 2013-05-13 | 1 | Anders | Bug fix: switch mode
|  | 2013-05-14 | 3 | Niklas | Working some with the UI, reading up on how to switch mode, and also designed a daymode and nighmode logo, and then realising it shouldnt even be two modes :P
|  | 2013-05-15 | 4 | Niklas | Working with the custom snippets, and a simple steptracker
|  | 2013-05-16 | 2.5 | Niklas | Continue working on the custom snippets, also looking in to a custom layers selection
|  | 2013-05-17 | 2 | Niklas | Refined the steptracker to one that actually works, refactored some code
|  | 2013-05-17 | 1.5 | Sofie | Tried to get virtual device working to simplify documentation but failed…
|  | 2013-05-18 | 4 | Niklas | Started working on iCal synchronization
|  | 2013-05-20 | 4 | Sofie | Went through lecture info, reasearched internet, other course docs, Max instructions etc. and setup User Manual, Developer Manual and Software Dev Document
|  | 2013-05-21 | 2.5 | Sofie | Went through rest of lectures (1-4) and identified material to be used in documentation, added in software dev doc
|  | 2013-05-22 | 6 | Fredrik | Fixed errors and added a bit
|  | 2013-05-23 | 6 | Fredrik | Most of the time I did refactor
|  | 2013-05-22 | 3 | Anders | Started working on navigation dialog
|  | 2013-05-23 | 8 | Anders | Fixing "My Position"-bug, added navigation dialog, added target positioning(available from long-click), presentation tool and more.